# background. - The Local Electoral Administration (Scotland) Act 2011 (S.4A) gives the Convener of the Electoral Management Board for Scotland (EMB) authority to make directions to Returning Officers (ROs) and Electoral Registration Officers (EROs) in relation to the exercise of your functions in delivering the Scottish Parliament election. # purpose of directions

- The EMB coordinates delivery of the election across Scotland with a focus on the interests of the voter.  The overall goal is to deliver results that will be accepted and trusted as accurate, resulting from election processes that are accessible, consistently delivered, efficient and secure.

- This goal is achieved through a consistent voter experience and a resilient approach to all planning and implementation.  Any Directions the Convener has determined as appropriate will assist ROs, EROs and other persons in carrying out their functions in pursuit of this aim.

# Development of the Directions

- The Convener has been making formal Directions to ROs and EROs to support the delivery of Scottish Parliament Elections since 2016 with informal recommendations made in 2011.  Directions covering Scottish Local Government Elections have been made by the Convener since 2012.

- Directions for the 2026 Scottish Parliament Election are based on significant precedent, taking account of the lessons learned by the whole community from previous events.  The experience of the administration of the UK Parliamentary General election in 2024, particularly the challenges around print and postal vote administration, has informed the development of these Directions.  They are further intended to anticipate risks and challenges that may arise.

# consultation

- As required by legislation, the Directions have been the subject of formal consultation within the EMB, which includes both ROs and EROs, and with the Electoral Commission.  The final Directions reflect issues identified and comments made in those consultations.

- There have also been informal discussions with print and IT contractors and with Royal Mail, to ensure that key suppliers are aware of the production schedules that will be required by the Directions.  The Directions, as draft proposals, were presented to ROs and EROs and Electoral Administrators at an event hosted by the EMB and Electoral Commission on 7 October with opportunity following the event for their comment and feedback.

- Following discussion at the conference, the EMB approved this final set of Directions at the end of October 2025.  Following the Board’s approval, The Convener is now content formally to make the Directions which are presented below. The table below provides a full statement of the Directions with a short commentary where clarification might be useful, as has been the convention with the Directions that have been made for previous elections.

# Gould Principle

- These Directions are being made formally on 3 November 2025 ahead of the 6-month window required by the Gould Principle.  The draft Directions have previously been widely circulated such that ROs and EROs have been able to incorporate them into their planning.

# accessibility. - In February 2024 in support of the delivery of the UK Parliamentary General Election the Convener of the EMB identified a series of recommended measures to be taken by ROs and EROs to improve the accessibility of elections. No specific direction is being made in this area for the Scottish Parliament Election in May 2026. However, the Electoral Commission is producing statutory guidance with respect to the accessibility of elections and the recent legislation (The Scottish Parliament (Elections etc.) (Miscellaneous Amendments) Order 2025 14(4D)) requires ROs to have regard to that guidance. - The general principles and actions that were identified in the February 2024 recommendations remain relevant and valid and ROs and EROs will wish to review those as they put their plans in place for May 2026. # scope for additional directions

- An effort has been made to minimise the number of Directions rather than adding to the rules.  That said, the Convener of the EMB may make additional Directions in response to new information or changes in circumstances affecting the election.  Any such Directions made would only be to support consistency of administration or to promote resilience and contingency.  Recognising the Gould Principle, additional Directions within 6 months of the election will be avoided if possible.

# ONgoing support

- The Convener, Members of the EMB, its officers and advisers are available to offer support and advice to ROs and EROs in the planning and delivery of the election.  The Board will also engage with the Electoral Commission to access intelligence gained from their performance standards processes.  This will support and inform the EMB’s own oversight of the planning and delivery of the election.

- The Convener gives a briefing at each SOLACE meeting, allowing Chief Executives collectively to consider election issues.  He is available to Returning Officers at that meeting or any other time to discuss concerns around the delivery of electoral events.  In addition, the broader community of electoral professionals in Scotland is supportive, experienced and willing to offer advice, expertise and support.

# BrIefing events seminars and other resources

- The EMB, jointly with the Electoral Commission, has planned a series of seminars for RO and ERO staff in the coming months to cover specific practical elements of planning for the delivery of the 7 May election.  All ROs and EROs should ensure that they are represented at these events.

- The Electoral Commission offers a suite of guidance, forms and resources to assist Returning Officers.  The EMB may also make available additional resources to both Regional and Constituency Returning Officers to assist in the administration of the election, including a template to allow RROs to calculate the allocation of seats for each Region.

# Directions from the ConVeNer of the emb

|  | ## Workstream | ## direction |
| --- | --- | --- |
| 1 | Ballot Papers Ballot Paper Colour | Ballot Papers for the Scottish Parliament election on 7 May 2026 are to be the same colours as were used in previous elections to the Scottish Parliament (2007, 2011, 2016 and 2021) i.e., PEACH (Regional Papers) and LILAC (Constituency Papers). Comment Each voter is issued with two ballot papers: a Regional Paper and a Constituency Paper. The Scottish Parliament (Elections etc.) Order 2015 only requires that the colours are different. Consideration has been given to the usual issues that affect the choice of colour for ballot papers, i.e. - a consistency of colours across Scotland to support national information and political campaigns; - a preference to avoid colours that are identified with political parties or particular policy campaigns; - an avoidance of colours or colour schemes that might prove challenging to those with visual impairment; and - a preference that colours should be clearly different from one another so that papers are easily distinguished in a “rummage” of boxes. Print production methods may vary with some suppliers using coloured paper and others a colour wash process, but for reference it is expected that the colours will conform to Lilac as Pantone 2692 and Peach as Pantone 138. |
| 2 | Notices Publication of Notice of Election | Returning Officers are directed to publish the Notice of Election on Monday 16 March 2026, allowing nominations to be taken from the following day, Tuesday 17 March 2026. Comment The Notice of Election can be published at any point between Monday 16 March and Wednesday 25 March. A uniform publication date across Scotland provides consistency around the start of the nominations period and assists planning for campaigners, candidates and agents. The consistency also supports communication with voters and general public awareness of key dates. An early date allows the nomination period to be as long as possible. This benefits candidates and agents and allows RO teams, especially those with responsibility for Regional nominations, to resource and plan for accepting nominations more effectively. |
| 3 | Poll Cards Date of dispatch of poll cards | Returning Officers should dispatch poll cards between Tuesday 17 March and Wednesday 18 March. Comment Legislation (Rule 24 Sch 2 Of the SP Order 2015) requires Returning Officers to issue poll cards as soon as is reasonably practicable after publishing the Notice of Election. This date would imply a registration deadline of around 6 February for a newly registered elector to be included in this first issue of poll cards. Pollcards will be issued on the basis of the March register and the deadline for inclusion in this register is 6 February. A two-day window is being directed rather than a single date to promote consistency in voter experience across Scotland while allowing flexibility for Returning Officers who work with different suppliers of key support services. |
| 4 | Absent Voting First dispatch of postal ballot packs | The first issue of postal votes should be dispatched, by first class post, between Wednesday 15 April and Friday 17 April. Comment Legislation states that postal ballot papers and postal voting statements should be issued as soon as is practicable. Nominations will close at 4pm on Wednesday 1 April 2026. A consistent date of dispatch/receipt by voters will support national communication and voter awareness activities by the RO and the Electoral Commission and allow political parties and others to plan their own campaigns. This would mean that if an elector who is already registered applies for a postal vote by 23 March, then it should be in this first issue. A consistent final issue date of postal votes will also be agreed. |
| 5 | Second Interim Election Notice of Alteration (SIENA) Publication Date | Electoral Registration Officers must publish the Second Interim Election Notice of Alteration (SIENA) on 10 April 2026. With publication of the SIENA on 10 April 2026, a second issue of postal votes is able to pick up those electors who have applied for a postal vote since the first issue, ensuring they get their postal packs as quickly as possible and do not have to wait until the final issue. This second issue would be dispatched around 20 April, but this direction is for a consistent SIENA publication rather than a consistent date of dispatch for the interim issue of postal votes. |
| 6 | Absent Voting Final Dispatch of Postal Votes | ROs must ensure that there is at least one additional issue of postal ballot packs. The final dispatch to all validly registered postal voters should be handed over from printers to the postal services on Tuesday 28 April using the Final Election Notice of Alteration (FENA) Comment Note the 5pm, Tuesday 21 April deadline for requests for a new postal vote or to change or cancel an existing postal vote or proxy appointment, for those electors who are already registered. This does not preclude ROs from issuing postal vote packs at other times if necessary, e.g. because an elector is going to be on holiday or away on business by the time of the next issue of postal votes, and the RO decides, as they can, to issue an individual postal vote pack. The postal ballot packs dispatched must include postal votes being sent to electors who are temporarily overseas e.g. on a holiday. There is no special provision for overseas voters, although their numbers will be limited under this franchise. There will be service voters and those away for holidays/students with overseas ballot paper addresses. |
| 7 | Ballot Papers Ballot Paper Numbering Protocol for Regional Ballot Papers | Regional Returning Officers must implement a ballot paper numbering protocol such that each paper is uniquely numbered, different from any other paper in that contest. Comment Ballot papers must be numbered such that each ballot paper is unique at the relevant poll. (Ballot paper numbers are distinct from the Unique Identifying Mark (UIM)) No specific recommendation is being given on how this should be achieved across the country and different approaches might be appropriate in different circumstances. Options for RROs would include the use of prefixes to the ballot paper number or allocations of sets of numbers to constituencies. The fundamental requirement is to ensure that no contest has multiple papers with the same number. |
| 8 | Ballot Papers Official Mark | The official mark on ballot papers issued in polling stations should be different from that on papers issued in postal vote packs. Comment The Scottish Parliament (Elections etc.) Order 2015 requires both Constituency and Regional ballot papers to carry an Official Mark. While the Official Mark is to be determined by the Constituency Returning Officer, RROs must ensure that the Mark is consistent across all Regional Papers. |
| 9 | Verification and Count Count Timing | Returning Officers must ensure that the first ballot boxes are opened at 9am on Friday 8 May 2026, to allow the verification and counting of constituency and regional ballot papers in their constituencies to begin. For the avoidance of doubt, there is to be no overnight verification of ballot boxes or counting of votes. If ROs choose to verify the unused, spoilt and postal votes at the close of poll and overnight, which they are free to do, then observers, candidates and their agents must be able to attend these processes. Comment For the Returning Officers and the EMB, the priority is the production of accurate results in which the voter can have full confidence. Accuracy is always more important than speed. For local government elections in Scotland a “next day count” is well-accepted procedure and acknowledged as allowing a greater level of resilience within Election Teams while supporting accuracy. The same arguments apply to elections to the Scottish Parliament and are further amplified given the complexities of handling two ballot papers and the need for communication between CROs and RROs for calculation of the Regional Result and seat allocation. The factors supporting the delivery of a next day count include: - accuracy of the process with a reduced scope for error from rested rather than fatigued staff; - resilience of systems and venues, with problems easier to resolve during daytime; - staff welfare, recognising that key members of the election teams will often have been working for well over 24 hours by the conclusion of an overnight count; - staff availability, with a daytime count freeing polling staff and others to assist at the count; - time to allow for the authentication of late postal votes which needs to be completed before verification can be concluded; and - better public engagement, with results coming through the late afternoon ready for the 6 pm news rather than throughout the early hours of the morning. There are well-engineered and tested controls in place for each verification/count operation to ensure that the results are correct. However, holding the count the day following the poll allows the effective use of fresh and rested staff. This in part mitigates the risk of any errors which would otherwise need to be corrected. Returning Officer planning must include an element of risk management, considering how we can best minimise the known challenges that we face in planning, preparation and delivery. An overnight count brings additional risk to an already complex process. |

# Performance monitoring

- It is not in the remit of the EMB to monitor the performance of ROs and EROs.  However, legislation gives the Convener power to make these Directions and ROs and EROs are required to comply with them as they would with the other election rules.  If an RO or ERO has any concerns about their ability to follow any of these Directions locally then they should raise this with the Convener of the EMB immediately and he will be happy to discuss. The Electoral Commission will monitor compliance with these Directions in their usual performance monitoring engagement and activity.

# Timetable for the Scottish Parliament election on Thursday 7 May 2026

- Under the Scottish Elections (Reform) Act 2020, an ordinary general election to the Scottish Parliament is required to be held no later than Thursday 7 May 2026. The date of the poll may be varied by up to a month by the monarch, on proposal by the Presiding Officer.  New legislation may affect the times and dates set out below.

- The days which are disregarded in calculating the timetable are Saturday, Sunday, bank holidays and any day appointed for public thanksgiving or mourning. The timetable may change in the event of days being appointed for public thanksgiving or mourning.

Timetable for the Scottish Parliament election on Thursday 7 May 2026

Under the Scottish Elections (Reform) Act 2020, an ordinary general election to the Scottish Parliament is required to be held no later than Thursday 7 May 2026. The date of the poll may be varied by up to a month by the monarch, on proposal by the Presiding Officer. New legislation may affect the times and dates set out below.

The days which are disregarded in calculating the timetable are Saturday, Sunday, bank holidays and any day appointed for public thanksgiving or mourning. The timetable may change in the event of days being appointed for public thanksgiving or mourning.

| # Event | # Working days before poll (deadline if not midnight) | # Date (deadline if not midnight) |
| --- | --- | --- |
| Publication of notice of election | Not later than 28 days and not earlier than 35 days | Between Monday 16 March and Wednesday 25 March DIRECTED AT 16 MARCH |
| Delivery of nomination papers | From the day after the publication of the notice of election until the 23rd day (4pm) | Not later than 4pm on any working day after publication of notice of election until 4pm on Wednesday 1 April |
| Deadline for delivery of nomination papers | 23 days (4pm) | 4pm on Wednesday 1 April |
| Deadline for withdrawals of nomination | 23 days (4pm) | 4pm on Wednesday 1 April |
| Making objections to nomination papers | During the hours allowed for delivery of nomination papers on the last day for their delivery and the hour following. No objection may be made in the afternoon of the last day except to a nomination paper delivered within 24 hours of the last time for its delivery. | Objections can only be made on Wednesday 1 April (until 5pm). Until 12 noon on Wednesday 1 April objections can be made to all delivered nominations Between 12 noon and 5pm on Wednesday 1 April objections can only be made to nominations delivered after 4pm on Tuesday 31 March |
| Deadline for the notification of appointment of election agents | 23 days (4pm) | 4pm on Wednesday 1 April |
| Publication of statement of persons nominated, including notice of poll and situation of polling stations | If no objections: on 23 days (at 5pm) If objection(s) are made: Not before objection(s) are disposed of but not later than 24 hours after the last time for delivery of nomination papers. | If no objections: at 5pm on Wednesday 1 April Objection(s) made not before objection(s) are disposed of but not later than 4pm on Thursday 2 April |
| Publication of first interim election notice of alteration | 23 days | Wednesday 1 April |
| Deadline for receiving applications for registration. | 12 days | Monday 20 April |
| Deadline for receiving new postal vote and postal proxy applications, and for changes to existing postal or proxy vote. | 11 days (5pm) | 5pm on Tuesday 21 April |
| Deadline for receiving new applications to vote by proxy (not postal proxy or emergency proxies) | 6 days (5pm) | 5pm on Tuesday 28 April |
| Publication of second interim election notice of alteration | Between 22 days and 6 days | Between Thursday 2 April and Tuesday 28 April (inclusive) DIRECTED AS 10 APRIL |
| Publication of final election notice of alteration | 5 days | Wednesday 29 April |
| Deadline for notification of appointment of polling and counting agents | 5 days | Wednesday 29 April |
| Deadline for notification of appointment of sub-agents | 2 days | Tuesday 5 May |
| Polling day | 0 (7am to 10pm) | 7am to 10pm on Thursday 7 May |
| Last time for re-issue of spoilt or lost postal votes. | 0 (5pm) | 5pm on Thursday 7 May |
| Deadline for emergency proxy applications | 0 (5pm) | 5pm on Thursday 7 May |
| Last time to alter the register due to clerical error or court appeal. | 0 (9pm) | 9pm on Thursday 7 May |

# Regional returning officer responsibilities*

| # Region | # Regional returning officer | # constituencies |
| --- | --- | --- |
| Central Scotland and Lothians West | North Lanarkshire | Airdrie; Almond Valley; Bathgate; Coatbridge and Chryston; Cumbernauld and Kilsyth; Falkirk East and Linlithgow; Falkirk West; Motherwell and Wishaw; Uddingston and Bellshill |
| Edinburgh and Lothians East | City of Edinburgh | East Lothian Coast and Lammermuirs; Edinburgh Central; Edinburgh Eastern, Musselburgh and Tranent; Edinburgh North Eastern and Leith; Edinburgh North Western; Edinburgh Northern; Edinburgh South Western; Edinburgh Southern; Midlothian North |
| Glasgow | Glasgow | Glasgow Anniesland; Glasgow Baillieston and Shettleston; Glasgow Cathcart and Pollok; Glasgow Central; Glasgow Easterhouse and Springburn; Glasgow Kelvin and Maryhill; Glasgow Southside; Rutherglen and Cambuslang |
| Highlands and Islands | Highland | Argyll and Bute; Caithness, Sutherland and Ross; Inverness and Nairn; Moray; Na h-Eileanan an Iar; Orkney Islands; Shetland Islands; Skye, Lochaber and Badenoch |
| Mid Scotland and Fife | Fife | Clackmannanshire and Dunblane; Cowdenbeath; Dunfermline; Fife North East; Kirkcaldy; Mid Fife and Glenrothes; Perthshire North; Perthshire South and Kinross-shire; Stirling |
| North East Scotland | Aberdeen City | Aberdeen Central; Aberdeen Deeside and North Kincardine; Aberdeen Donside; Aberdeenshire East; Aberdeenshire West; Angus North and Mearns; Angus South; Banffshire and Buchan Coast; Dundee City East; Dundee City West |
| South Scotland | Dumfries and Galloway | Ayr; Carrick, Cumnock and Doon Valley; Clydesdale; Dumfriesshire; East Kilbride; Ettrick, Roxburgh and Berwickshire; Galloway and West Dumfries; Hamilton, Larkhall and Stonehouse; Kilmarnock and Irvine Valley; Midlothian South, Tweeddale and Lauderdale |
| West Scotland | Renfrewshire | Clydebank and Milngavie; Cunninghame North; Cunninghame South; Dumbarton; Eastwood; Inverclyde; Paisley; Renfrewshire North and Cardonald; Renfrewshire West and Levern Valley; Strathkelvin and Bearsden |

| # Constituency Name | # Returning Officer* |
| --- | --- |
| Aberdeen Central | Aberdeen City |
| Aberdeen Deeside and North Kincardine | Aberdeen City |
| Aberdeen Donside | Aberdeen City |
| Aberdeenshire East | Aberdeenshire |
| Aberdeenshire West | Aberdeenshire |
| Banffshire and Buchan Coast | Aberdeenshire |
| Angus North and Mearns | Angus |
| Angus South | Angus |
| Argyll and Bute | Argyll and Bute |
| Edinburgh Central | City of Edinburgh |
| Edinburgh North Eastern and Leith | City of Edinburgh |
| Edinburgh North Western | City of Edinburgh |
| Edinburgh Northern | City of Edinburgh |
| Edinburgh South Western | City of Edinburgh |
| Edinburgh Southern | City of Edinburgh |
| Clackmannanshire and Dunblane | Clackmannanshire |
| Dumfriesshire | Dumfries and Galloway |
| Galloway and West Dumfries | Dumfries and Galloway |
| Dundee City East | Dundee City |
| Dundee City West | Dundee City |
| Kilmarnock and Irvine Valley | East Ayrshire |
| Carrick, Cumnock and Doon Valley | East Ayrshire |
| Strathkelvin and Bearsden | East Dunbartonshire |
| East Lothian Coast and Lammermuirs | East Lothian |
| Edinburgh Eastern, Musselburgh and Tranent | East Lothian |
| Eastwood | East Renfrewshire |
| Falkirk East and Linlithgow | Falkirk |
| Falkirk West | Falkirk |
| Cowdenbeath | Fife |
| Dunfermline | Fife |
| Fife North East | Fife |
| Kirkcaldy | Fife |
| Mid Fife and Glenrothes | Fife |
| Glasgow Anniesland | Glasgow City |
| Glasgow Baillieston and Shettleston | Glasgow City |
| Glasgow Cathcart and Pollok | Glasgow City |
| Glasgow Central | Glasgow City |
| Glasgow Easterhouse and Springburn | Glasgow City |
| Glasgow Kelvin and Maryhill | Glasgow City |
| Glasgow Southside | Glasgow City |
| Caithness, Sutherland and Ross | Highland |
| Inverness and Nairn | Highland |
| Skye, Lochaber and Badenoch | Highland |
| Inverclyde | Inverclyde |
| Midlothian North | Midlothian |
| Moray | Moray |
| Na h-Eileanan an Iar | Na h-Eileanan an Iar |
| Cunninghame North | North Ayrshire |
| Cunninghame South | North Ayrshire |
| Uddingston and Bellshill | North Lanarkshire |
| Airdrie | North Lanarkshire |
| Coatbridge and Chryston | North Lanarkshire |
| Cumbernauld and Kilsyth | North Lanarkshire |
| Motherwell and Wishaw | North Lanarkshire |
| Orkney Islands | Orkney Islands |
| Perthshire North | Perth and Kinross |
| Perthshire South and Kinross-shire | Perth and Kinross |
| Paisley | Renfrewshire |
| Renfrewshire North and Cardonald | Renfrewshire |
| Renfrewshire West and Levern Valley | Renfrewshire |
| Ettrick, Roxburgh and Berwickshire | Scottish Borders |
| Midlothian South, Tweeddale and Lauderdale | Scottish Borders |
| Shetland Islands | Shetland Islands |
| Ayr | South Ayrshire |
| Clydesdale | South Lanarkshire |
| East Kilbride | South Lanarkshire |
| Hamilton, Larkhall and Stonehouse | South Lanarkshire |
| Rutherglen and Cambuslang | South Lanarkshire |
| Stirling | Stirling |
| Clydebank and Milngavie | West Dunbartonshire |
| Dumbarton | West Dunbartonshire |
| Almond Valley | West Lothian |
| Bathgate | West Lothian |

*Designation of Returning Officers according to The Scottish Parliament Elections (Regional Returning Officers and Constituency Returning Officers) Order 2025