| Contents. - Kit Delivery - Progress (page 1) - Use of New Software in By-Elections (page 1) - Returning Officer Engagement (page 1) - Local Authority Training (page 2) - Print Workstream (page 2) - Project User Group (page 2) Key Messages. - eCounting system used successfully in by-elections for Highland and Aberdeen City Councils - All local authority kick-off sessions with Regional Project managers completed Upcoming dates. EMB/EC Conference – Second date for split meeting Tuesday 24th November – 200 SVS Conference & Events, Glasgow Project Board (Meeting 6) – Wednesday 2nd December, 2 p.m. (online) Project Progress. Exit from Stage 3 is in process of being signed off. Work ongoing on training materials. Project Contact Details. James Newman Contract Manager/Elections Policy Lead james.newman@gov.scot 07780 900836 Liz Ure Digital Consultant/Technical Lead liz.ure@gov.scot 07769 239206 Mike Melville eCounting Project Manager mike.melville@gov.scot 07471 799630 Dougie McGregor Local Government Liaison/ EMB representative dougie.mcgregor@edinburgh.gov.uk 07938 978619 CGI Support eCounting2027Support@cgi.com | Kit Delivery - Progress. All orders for election kit have been placed, including the more recent request for colour printers. All scanners, PCs, servers and switches are in stock, as is the majority of printers, UPS, TVs and smartcards. The remaining kit is being shipped by the manufacturers and should all be delivered by mid-November. Use of New Software in By-Elections. The software for next year’s election was recently used in a live environment for the first time at by-elections to the Highland Council (1 October) and Aberdeen City Council (8 October). The by-elections demonstrated that the improvement in the ICR engine has resulted in lower adjudication rates than previously: Council; No of candidates; Adjudication rate. Highland; 5; 6.6%. Aberdeen City; 6; 9.5%. The integration of the former RO app into the system was well received and overall both election teams were happy with the performance of the system at their count. Returning Officer Engagement. Returning Officer engagement is progressing well: Kick-off meetings – 32/32 completed Site visits – 29/32 completed The outstanding site visits are due to be completed by mid-November. Returning Officers and their teams should now be receiving regular updates from their Regional Project Manager on progress in relation to their count. Local Authority Training. The provisional Edinburgh venue for the training in February (Sirius House) has unfortunately fallen through but the neighbouring Vega Building has been secured as a replacement. The Q&A documents and Factsheets used in the 2022 project are being reviewed and will start to be shared with Returning Officers and their teams before the end of the year. Progress continues to be made on the online elections training and the Elections Delivery Manual and dates for the availability of the online training will be notified in the next few weeks. Print Workstream. The third meeting of the Print Working Group on Wednesday 30 September agreed the final templates for postal packs and ballot papers. Poll cards, which are not part of the project, should be agreed between election teams and their normal print suppliers. Project User Group. Meeting 4 of the User Group was held online on Wednesday 28th October and Tuesday 3rd November. One of the key issues discussed was the banding of ballot books. Feedback from local authorities who have used the banded books at recent by-elections was positive and the matter will be reported to the next meeting of the Project Board on 2 December. Examples of the banded books will be available at the EMB/EC seminar on 2 November 2026. Next edition. The next edition of the Bulletin will be issued in November. |
| --- | --- |