## Guide
Scottish Local Government By-Election Timetable Calculator
1 | This spreadsheet can be used in one of two ways
Timetable Generator
i | If you know which date you want to hold a by-election, go to Timetable Generator. Select the cell for poll date and then Use the "Drop down date selector" to select the polling day desired. Elections timetable will pre-fill the dates. Fill in other blanks as required. Timetable is set up for printing in A4 format.
ii | If you don't know which date you want to hold a by-election and want to look at options go to "Main Dates Overview". This will show every set of dates for every Thursday between now and November 2021 which is six months prior to the next local government election. Christmas periods are highlighted in red for ease and some Thursdays which are on Dies Non or in Christmas periods have been removed.
There is a small calculator in the sheet to also show the last possible date a by-election can be held based on the date of resignation. This allows you to look at a range of different poll dates and decide a date based on local factors such as existing school holidays, school in-service days, large major events and council meetings and in the event of an elected member death, the funeral date.
2 | Notes on the how the days are calculated are highlighted in the 'notes' sheet showing Dies non.
3 | If any errors are detected or require rectified please contact
election.enquiries@moray.gov.uk
4 | No responsibility will be taken for reliance on the data to form election timetables and should be used as a guide only. ¦It is correct at time of publication but proclamations of additional public holidays can be made at any time which will affect Dies Non and the calculator.
Moray2020

## Timetable Generator
_______________ | Council
Local Government By-Election |  |  |  | Enter name of council
Ward ______________ | __________ |  |  | Enter Ward no. and name
Election Timetable
Date of Poll – | Select poll date here |  |  | SELECT CELL FIRST, it will edge highlight in blue, then using the drop down arrow,
First day to publish the notice of election | -35 | Not earlier than |  | select Date of Poll, assumed to be a Thursday
#VALUE!
Delivery of nomination papers | -34 | Each working day (between 10.00am and 4.00pm) from
#VALUE!
Last day to publish notice of election | -28 | Not later than
#VALUE!
Deadline for the delivery of nomination papers | -23 | Not later than 4.00pm on
Deadline for withdrawal of nomination | -23 | #VALUE!
Deadline for notification of appointment of election agents | -23
Publication of notice of poll | -23 | As soon as practicable after 4.00pm on
#VALUE!
Issue of Voter’s Pollcards | n/s |  | Enter per local arrangements
Registration deadline | -12 | Midnight on
#VALUE!
Deadline for new postal vote applications and for changes to existing postal or proxy votes | -11 | Not later than 5.00pm on
#VALUE!
Issue of Postal Votes | n/s |  | Enter per local arrangements, n/s - not statutory, as soon as practicable
Deadline for new applications to vote by proxy (not postal proxy), except for medical emergencies | -6 | Not later than 5.00pm on
#VALUE!
Deadline for notification of appointment of polling and counting agents | -5 | #VALUE!
First date that electors can apply for replacements for lost postal votes | -4 | #VALUE!
POLLING DAY | 0 | 7.00am – 10.00pm on
Select poll date here
Last time for re-issue of spoilt and lost postal votes | 0 | Not later than 5.00pm on
Select poll date here
Deadline for emergency proxy applications | 0 | Not later than 5.00pm on
Select poll date here
Last time to alter the register due to clerical error or court appeal | 0 | Not later than 9.00pm on
Select poll date here
COUNT | - | From 10am on | Enter start time of count
|  | #VALUE! | Assumed that the Count is held the next day ‘or overtype time and date’
Last day to submit election spending returns | +35d | #VALUE! | Assumed that the Count is held the next day and result declared one day after poll
Note on C43: Alison Davidson: 35 calendar days

## Main dates overview
Local Government By-Election Timetable Reckoner
Notes: Christmas Period is shown in Red Text
| Enter confirmed effective date of resignation |  |  | dd/mm/yyyy
| Latest date to hold a by-election | Enter Date Above
| Disclaimer: Dates in this tool are a guide only. All dates must be checked on use. | [10 empty] | See comment
Days | POLLING DAY | time axis 2020-03-05 to 2021-11-04
-35 | First date for publication of the Notice of election | -35 | [86 empty] | Six month rule applies prior to May 2022 Loal Government Elections | time axis 2020-01-16 to 2021-09-16
-34 | Earliest time Nomination period can commence | -34 | time axis 2020-01-17 to 2021-09-17
-28 | Lastest date for publication of the Notice of election | -28 | time axis 2020-01-27 to 2021-09-27
-27 | Latest time Nomination Period can commence | -27 | time axis 2020-01-28 to 2021-09-28
-23 | Deadline for lodging Nomination Papers - Not later than 4.00pm on | -23 | time axis 2020-02-03 to 2021-10-04
-23 | Deadline for lodging appointment of Election Agents - Not later than 4.00pm on | -23 | time axis 2020-02-03 to 2021-10-04
-23 | Latest time for withdrawal of Nomination Paper - Not later than 4.00pm on | -23 | time axis 2020-02-03 to 2021-10-04
-23 | Publish statement as to persons and parties nominated / notice of poll / notice of situation of polling stations or Notice in case of uncontested election (After 4.00pm) | -23 | time axis 2020-02-03 to 2021-10-04
-21 | First Issue of Pollcards | -21 | time axis 2020-02-05 to 2021-10-06
-12 | Last day for applications to be included on the register of electors to be used at these elections | -12 | time axis 2020-02-18 to 2021-10-19
-11 | Deadline for requests for a new postal vote or to change or cancel an existing postal vote or proxy appointment - Not later than 5.00pm on | -11 | time axis 2020-02-19 to 2021-10-20
-9 | Second Issue of pollcards | -9 | time axis 2020-02-21 to 2021-10-22
-8 | Postal Vote Issue by | -8 | time axis 2020-02-24 to 2021-10-25
-6 | Postal Vote Opening commences on | -6 | time axis 2020-02-26 to 2021-10-27
-6 | Deadline for new applications to vote by proxy (not postal proxy), except for medical emergencies - Not later than 5.00pm on | -6 | time axis 2020-02-26 to 2021-10-27
-5 | Last day for the appointment of Polling and Counting Agents | -5 | time axis 2020-02-27 to 2021-10-28
-4 | First day to issue ballot papers in response to requests to replace lost postal ballot papers | -4 | time axis 2020-02-28 to 2021-10-29
0 | Deadline for the issue of replacement for spoilt or lost postal ballot papers - Not later than 5.00pm on | 0 | time axis 2020-03-05 to 2021-11-04
0 | Deadline for new applications to vote by proxy on the grounds of a medical emergency - Not later than 5.00pm on | 0 | time axis 2020-03-05 to 2021-11-04
0 | Last day to make alterations to the register to correct a clerical error or to implement a court (registration appeal) decision - Not later than 9.00pm on | 0 | time axis 2020-03-05 to 2021-11-04
0 | Polling Day (7.00am - 10.00pm) | 0 | time axis 2020-03-05 to 2021-11-04
1 | Verification and Counting of votes (if held next day) | 1 | time axis 2020-03-06 to 2021-11-05
35 | Latest date for delivery of return of declarations as to election expenses | 35 | time axis 2020-04-10 to 2021-12-10
[7 empty] | VE DAY |  |  |  |  | Fri 8 May 2020 is
VE DAY
Note on A31: Alison Davidson: 35 calendar days

## Notes and disclaimer
1 | The Scottish Local Government Elections Order 2011
| Schedule 1 (1)(2) |  | designates Saturday, Sunday, Christmas Eve, Christmas Day, Good Friday, Easter Monday
|  | and | designates a day which is a Bank holiday in Scotland under Banking & Financial Dealings Act 1971;
|  | and | day appointed for public thanksgiving and mourning (this requires a Royal Proclamation)
2 | Scottish Government list |  | for Scottish list of public holidays
3 | See London Gazette |  | for royal proclamation of bank holidays, mourning etc.
(this sheet does not account for days that announced ad-hoc)
4 | St Andrews Day Bank Holiday (Scotland) Act 2007
If 30 November occurs on a weekend, the bank holiday is moved to the following Monday.
5 | If a bank holiday falls on a Saturday or Sunday, a substitute weekday becomes a bank holiday (usually the following Monday).
6 | Banking and Financial Dealings Act 1971 |  |  | See schedule 1
The following are to be bank holidays in Scotland:—E+W+S+N.I.
New Year’s Day, if it be not a Sunday or, if it be a Sunday, 3rd January.
2nd January, if it be not a Sunday or, if it be a Sunday, 3rd January.
Good Friday
The first Monday in May.
The first Monday in August.
Christmas Day, if it be not a Sunday or, if it be a Sunday, 26th December.
7 | Boxing Day became a Bank Holiday in Scotland by Royal Proclamation on 18 October 1974
| So | Saturdays and Sundays are ruled out by SLGEO 2011
New Years Day (1 Jan) is ruled out by BFD Act 1971
2nd January is ruled out by BFD Act 1971
Good Friday is ruled out by BFD Act 1971 abd SLGEO 2011
Easter Monday is ruled out by SLGEO 2011 (but not BFD Act 1971)
|  | Early May Holiday is ruled out by BFD Act 1971, it moves in 2020 from 4 May to 8 May due to 75th anniversary of VE day under Royal proclamation |  |  | https://www.thegazette.co.uk/notice/3330529.
Spring Bank Holiday set subject to Royal Proclamation, in addition to those in Sch. 1 Financial Dealings Act 1971
Early August Holiday is ruled out by BFD Act 1971
30 November (or next available weekday) is ruled out by St Andrews Day Bank Holiday (Scotland) Act 2007
Christmas Eve (24 Dec) is ruled out by SLGEO 2011 if it is weekday or the weekend
Christmas Day (25 Dec) is ruled out by BFD Act 1971 and SLGEO 2011
Boxing Day (26 Dec) is ruled out by Royal Proclamation on 18 October 1974
Disclaimer |  | The information found on this spreadsheet is intended to be used as a tool to generate dates in local government by-elections
No liability by the author is assumed for the accuracy of the data given or generated herein.
Administrators must undertake their own checks and consult the relevant up to date legal references before publishing their elections timetable.

## non workdays
| Date | Day | Reason | Reference |  | Poll Dates
1 | 2020-02-01 | Sat | Weekend | SLGEO 2011 |  | Select poll date here | This sheet is for formula reference only.
2 | 2020-02-02 | Sun | Weekend | SLGEO 2011 |  | 2020-03-05
3 | 2020-02-08 | Sat | Weekend | SLGEO 2011 |  | 2020-03-12
4 | 2020-02-09 | Sun | Weekend | SLGEO 2011 |  | 2020-03-19
5 | 2020-02-15 | Sat | Weekend | SLGEO 2011 |  | 2020-03-26
6 | 2020-02-16 | Sun | Weekend | SLGEO 2011 |  | 2020-04-02
7 | 2020-02-22 | Sat | Weekend | SLGEO 2011 |  | 2020-04-09
8 | 2020-02-23 | Sun | Weekend | SLGEO 2011 |  | 2020-04-16
9 | 2020-02-29 | Sat | Weekend | SLGEO 2011 |  | 2020-04-23
10 | 2020-03-01 | Sun | Weekend | SLGEO 2011 |  | 2020-04-30
11 | 2020-03-07 | Sat | Weekend | SLGEO 2011 |  | 2020-05-07
12 | 2020-03-08 | Sun | Weekend | SLGEO 2011 |  | 2020-05-14
13 | 2020-03-14 | Sat | Weekend | SLGEO 2011 |  | 2020-05-21
14 | 2020-03-15 | Sun | Weekend | SLGEO 2011 |  | 2020-05-28
15 | 2020-03-21 | Sat | Weekend | SLGEO 2011 |  | 2020-06-04
16 | 2020-03-22 | Sun | Weekend | SLGEO 2011 |  | 2020-06-11
17 | 2020-03-28 | Sat | Weekend | SLGEO 2011 |  | 2020-06-18
18 | 2020-03-29 | Sun | Weekend | SLGEO 2011 |  | 2020-06-25
19 | 2020-04-04 | Sat | Weekend | SLGEO 2011 |  | 2020-07-02
20 | 2020-04-05 | Sun | Weekend | SLGEO 2011 |  | 2020-07-09
21 | 2020-04-11 | Sat | Weekend | SLGEO 2011 |  | 2020-07-16
22 | 2020-04-12 | Sun | Weekend | SLGEO 2011 |  | 2020-07-23
23 | 2020-04-18 | Sat | Weekend | SLGEO 2011 |  | 2020-07-30
24 | 2020-04-19 | Sun | Weekend | SLGEO 2011 |  | 2020-08-06
25 | 2020-04-25 | Sat | Weekend | SLGEO 2011 |  | 2020-08-13
26 | 2020-04-26 | Sun | Weekend | SLGEO 2011 |  | 2020-08-20
27 | 2020-05-02 | Sat | Weekend | SLGEO 2011 |  | 2020-08-27
28 | 2020-05-03 | Sun | Weekend | SLGEO 2011 |  | 2020-09-03
29 | 2020-05-09 | Sat | Weekend | SLGEO 2011 |  | 2020-09-10
30 | 2020-05-10 | Sun | Weekend | SLGEO 2011 |  | 2020-09-17
31 | 2020-05-16 | Sat | Weekend | SLGEO 2011 |  | 2020-09-24
32 | 2020-05-17 | Sun | Weekend | SLGEO 2011 |  | 2020-10-01
33 | 2020-05-23 | Sat | Weekend | SLGEO 2011 |  | 2020-10-08
34 | 2020-05-24 | Sun | Weekend | SLGEO 2011 |  | 2020-10-15
35 | 2020-05-30 | Sat | Weekend | SLGEO 2011 |  | 2020-10-22
36 | 2020-05-31 | Sun | Weekend | SLGEO 2011 |  | 2020-10-29
37 | 2020-06-06 | Sat | Weekend | SLGEO 2011 |  | 2020-11-05
38 | 2020-06-07 | Sun | Weekend | SLGEO 2011 |  | 2020-11-12
39 | 2020-06-13 | Sat | Weekend | SLGEO 2011 |  | 2020-11-19
40 | 2020-06-14 | Sun | Weekend | SLGEO 2011 |  | 2020-11-26
41 | 2020-06-20 | Sat | Weekend | SLGEO 2011 |  | 2020-12-03
42 | 2020-06-21 | Sun | Weekend | SLGEO 2011 |  | 2020-12-10
43 | 2020-06-27 | Sat | Weekend | SLGEO 2011 |  | 2020-12-17
44 | 2020-06-28 | Sun | Weekend | SLGEO 2011 |  | 2021-01-07
45 | 2020-07-04 | Sat | Weekend | SLGEO 2011 |  | 2021-01-14
46 | 2020-07-05 | Sun | Weekend | SLGEO 2011 |  | 2021-01-21
47 | 2020-07-11 | Sat | Weekend | SLGEO 2011 |  | 2021-01-28
48 | 2020-07-12 | Sun | Weekend | SLGEO 2011 |  | 2021-02-04
49 | 2020-07-18 | Sat | Weekend | SLGEO 2011 |  | 2021-02-11
50 | 2020-07-19 | Sun | Weekend | SLGEO 2011 |  | 2021-02-18
51 | 2020-07-25 | Sat | Weekend | SLGEO 2011 |  | 2021-02-25
52 | 2020-07-26 | Sun | Weekend | SLGEO 2011 |  | 2021-03-04
53 | 2020-08-01 | Sat | Weekend | SLGEO 2011 |  | 2021-03-11
54 | 2020-08-02 | Sun | Weekend | SLGEO 2011 |  | 2021-03-18
55 | 2020-08-08 | Sat | Weekend | SLGEO 2011 |  | 2021-03-25
56 | 2020-08-09 | Sun | Weekend | SLGEO 2011 |  | 2021-04-01
57 | 2020-08-15 | Sat | Weekend | SLGEO 2011 |  | 2021-04-08
58 | 2020-08-16 | Sun | Weekend | SLGEO 2011 |  | 2021-04-15
59 | 2020-08-22 | Sat | Weekend | SLGEO 2011 |  | 2021-04-22
60 | 2020-08-23 | Sun | Weekend | SLGEO 2011 |  | 2021-04-29
61 | 2020-08-29 | Sat | Weekend | SLGEO 2011 |  | 2021-05-06
62 | 2020-08-30 | Sun | Weekend | SLGEO 2011 |  | 2021-05-13
63 | 2020-09-05 | Sat | Weekend | SLGEO 2011 |  | 2021-05-20
64 | 2020-09-06 | Sun | Weekend | SLGEO 2011 |  | 2021-05-27
65 | 2020-09-12 | Sat | Weekend | SLGEO 2011 |  | 2021-06-03
66 | 2020-09-13 | Sun | Weekend | SLGEO 2011 |  | 2021-06-10
67 | 2020-09-19 | Sat | Weekend | SLGEO 2011 |  | 2021-06-17
68 | 2020-09-20 | Sun | Weekend | SLGEO 2011 |  | 2021-06-24
69 | 2020-09-26 | Sat | Weekend | SLGEO 2011 |  | 2021-07-01
70 | 2020-09-27 | Sun | Weekend | SLGEO 2011 |  | 2021-07-08
71 | 2020-10-03 | Sat | Weekend | SLGEO 2011 |  | 2021-07-15
72 | 2020-10-04 | Sun | Weekend | SLGEO 2011 |  | 2021-07-22
73 | 2020-10-10 | Sat | Weekend | SLGEO 2011 |  | 2021-07-29
74 | 2020-10-11 | Sun | Weekend | SLGEO 2011 |  | 2021-08-05
75 | 2020-10-17 | Sat | Weekend | SLGEO 2011 |  | 2021-08-12
76 | 2020-10-18 | Sun | Weekend | SLGEO 2011 |  | 2021-08-19
77 | 2020-10-24 | Sat | Weekend | SLGEO 2011 |  | 2021-08-26
78 | 2020-10-25 | Sun | Weekend | SLGEO 2011 |  | 2021-09-02
79 | 2020-10-31 | Sat | Weekend | SLGEO 2011 |  | 2021-09-09
80 | 2020-11-01 | Sun | Weekend | SLGEO 2011 |  | 2021-09-16
81 | 2020-11-07 | Sat | Weekend | SLGEO 2011 |  | 2021-09-23
82 | 2020-11-08 | Sun | Weekend | SLGEO 2011 |  | 2021-09-30
83 | 2020-11-14 | Sat | Weekend | SLGEO 2011 |  | 2021-10-07
84 | 2020-11-15 | Sun | Weekend | SLGEO 2011 |  | 2021-10-14
85 | 2020-11-21 | Sat | Weekend | SLGEO 2011 |  | 2021-10-21
86 | 2020-11-22 | Sun | Weekend | SLGEO 2011 |  | 2021-10-28
87 | 2020-11-28 | Sat | Weekend | SLGEO 2011 |  | 2021-11-04
88 | 2020-11-29 | Sun | Weekend | SLGEO 2011
89 | 2020-12-05 | Sat | Weekend | SLGEO 2011
90 | 2020-12-06 | Sun | Weekend | SLGEO 2011
91 | 2020-12-12 | Sat | Weekend | SLGEO 2011
92 | 2020-12-13 | Sun | Weekend | SLGEO 2011
93 | 2020-12-19 | Sat | Weekend | SLGEO 2011
94 | 2020-12-20 | Sun | Weekend | SLGEO 2011
95 | 2020-04-10 | Fri | Good Friday | SLGEO 2011
96 | 2020-04-13 | Mon | Easter Monday | SLGEO 2011
97 | 2020-05-08 | Fri | Early May Holiday | Royal Proclamation | Moved to coincide with 75th VE Day
98 | 2020-05-25 | Mon | Spring Bank Holiday | Royal Proclamation
99 | 2020-08-03 | Mon | August Bank Holiday | Scotland
100 | 2020-11-30 | Mon | St Andrews Day | Scotland
101 | 2020-12-24 | Thu | Christmas Eve | SLGEO 2011
102 | 2020-12-25 | Fri | Christmas Day | SLGEO 2011
103 | 2020-12-28 | Mon | Boxing Day | SLGEO 2011
104 | 2021-01-01 | Fri | New Years Day | BFD Act 1971
105 | 2021-01-04 | Mon | Scottish Public Holiday | SLGEO 2011 | Moved from Saturday 2 January
106 | 2021-04-02 | Fri | Good Friday | SLGEO 2011
107 | 2021-04-05 | Mon | Easter Monday | SLGEO 2011
108 | 2021-05-03 | Mon | Early May Holiday | Royal Proclamation
109 | 2021-05-31 | Mon | Spring Bank Holiday | Royal Proclamation
110 | 2021-08-02 | Mon | August Bank Holiday | Scotland
111 | 2021-11-30 | Tue | St Andrews Day | Scotland
112 | 2021-12-24 | Fri | Christmas Eve | SLGEO 2011
113 | 2021-12-27 | Mon | Christmas Day | SLGEO 2011 | Moved from Saturday 25 Dec
114 | 2021-12-28 | Tue | Boxing Day | SLGEO 2011 | Moved from Sunday 26 Dec
115 | 2022-01-03 | Mon | New Years Day | BFD Act 1971 | Moved from Saturday 1 Jan
116 | 2022-01-04 | Tue | Scottish Public Holiday | SLGEO 2011 | Moved from Sunday 2 Jan
117 | 2022-04-15 | Fri | Good Friday | SLGEO 2011
118 | 2022-04-18 | Mon | Easter Monday | SLGEO 2011
119 | 2022-05-02 | Mon | Early May Holiday | Royal Proclamation
120 | 2022-05-30 | Mon | Spring Bank Holiday | Royal Proclamation
121 |  |  | August Bank Holiday | Scotland
122 |  |  | St Andrews Day | Scotland
123 |  |  | Christmas Eve | SLGEO 2011
124 |  |  | Christmas Day | SLGEO 2011
125 |  |  | Boxing Day | SLGEO 2011
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Formulas:
Poll Dates = [Poll Dates, row above]+7