ACTION NOTE

EXTRAORDINARY MEETING OF THE EMB: PLANNING AND PREPARATION FOR THE EUROPEAN PARLIAMENTARY ELECTIONS 23 MAY 2019 TELEPHONE CONFERENCE

| Date | 1 May 2019 |
| --- | --- |
| Time | 1600 |

- Note of Previous Meeting 25 April 2019 (circulated) - Accepted as accurate

  - Apologies / Matters Arising – none noted

- Risk Register

Noted.  Focus was on risks showing Amber.  Primary concerns relate to delivery at short notice and limited funds / staffing.

- Governance / Process

  - Nominations; ballot paper; UIM, Official Mark  Noted

  - Notices – SOPN – position noted that SPN created in two forms.  Home addresses redacted from version to be published on line.

  - Agents, Sub Agents, Local Sub-Agents – notices of agents, subagents circulated;  note that some parties appointing few subagents locally

  - Briefings for candidates/agents -   offered to national agents.  Little interest

  - Count Collation (material circulated for test on 13 May) noted.

- Directions – Poll Cards now out, Postal Votes next week

- Registration issues – SAA update – key issue is transforming G electors into K electors and challenges of processing forms in time.  Polling staff training should emphasise the need to be prepared for EU citizens who may still be G electors and thus not enfranchised for this poll.

- Costs

  - Fees and Charges – advances Fees and Charges Order made.  Advances to follow when processed

  - Treatment of staff fees in the event of cancellation update from ECAB – If staff appointed then “it would not be unreasonable to pay them” in the event of cancellation.  CH to update LROs

- Integrity / Police SPOC – update from Supt Pat O’Callaghan.  Command Structure in place.  No specific intelligence of threat to election

- Additional Guidance / support – Adjudication, Personation guidance – discussion around hypothetical situation of voters writing “Brexit” on the Ballot Paper – as has been promoted on Social Media

  - Bulletins (circulated) Noted

- Public Awareness – Electoral Commission, European Parliament, LROs  Noted

- Media

- Legal Issues

- AOB