## Consultation
Consultation | Action | Date
Public Health Scotland
Local IJB
Local Resilience/Contingency Planning
Local Health and Safety

## Lists
Status | Risk Category | Lead Officer | Strategic Lead | Impact (H,M,L) | Risk Threat | Initial Risk Score | Control Actions
Open | Financial Resilience | Insert Name | Insert Name | High | Remote Operational Delivery
Closed | Supply Chain | Insert Name | Insert Name | Med | Reduced Capacity
| Venues | Insert Name | Insert Name | Low
| Workforce Protection and Planning | Insert Name | Insert Name
| Electoral Registration | Insert Name | Insert Name
| Nominations | Insert Name | Insert Name
| Voting In-Person | Insert Name | Insert Name
| Absent Voting | Insert Name | Insert Name
| The Count | Insert Name | Insert Name

## By-Election Risks
Risk Description | Risk Workstream | Planning Assumptions | Risk Owner | Impact (H,M,L) | Status | Control Actions | % Complete | Target Completion Date
Increase in financial costs of running a Council by-election under the rules of social distancing | Financial Resilience | There is no additional funding available from the Scottish government to conduct a Council by-election under the rules of social distancing. |  | Low | Open | Estimate a likely range in costs
Contractors and suppliers have ceased trading or do not have the capacity to deliver required services | Supply Chain Stabilisation |  |  | High | Open | Communication with suppliers, determine where contingency planning is required
Venues remain available and are suitable for the requirements of elections with social distancing | Venues |  |  | Med | Open | Make contact with venue, determine facilities meet with new requirements, visit where necessary
Sufficient quantities of trained staff are available and their health & safety is appropriately protected | Workforce Protection and Planning |  |  | High | Open | Determine requirements, availability and protection measures
The Electoral Registration Office has the capacity to deliver services with the requirements of social distancing and the likely increase in postal votes | Electoral Registration |  |  | High | Open | Follow up on previous feedback and communications
To effectively protect staff, candidates and agents and implement appropriate Health & Safety measures throughout the nomination process | Nominations |  |  | Med | Open | Devise and implement processes that meet the requirements of social distancing
To effectively protect staff, candidates and agents and implement appropriate Health & Safety measures within Polling Places | Voting In-Person |  |  | High | Open | Devise and implement processes that meet the requirements of social distancing
To effectively protect staff, candidates and agents and implement appropriate Health & Safety measures throughout the process of managing postal votes | Absent Voting |  |  | High | Open | Devise and implement processes that meet the requirements of social distancing
To effectively protect staff, candidates and agents and implement appropriate Health & Safety measures throughout the count process | The Count |  |  | High | Open | Devise and implement processes that meet the requirements of social distancing

## Financial Resilience
Elections and Covid-19 - FINANCIAL RESILIENCE
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1.1 | PPE, Hygiene and Cleaning Costs | Initial and ongoing venue cleaning (cleaning products, staffing costs)
1.2 |  | Protective plastic barriers for customer facing staff |  |  | Consider for polling places, postal vote opening and the count
1.3 |  | Hand Sanitiser
Face coverings / masks
2.1 | Absent Voting Costs | Number of postal votes to be produced
2.2 |  | Number of issues, consider an additional 2nd issue
2.3 |  | Postage costs for increased volumes
2.4 |  | Additional postal vote opening staff
2.5 |  | Bigger venue / longer booking period
2.6 |  | Additional reserve postal vote opening staff
3.1 | Polling Place Costs | Longer booking time to include the day prior for set-up
3.2 |  | Additional Information Posters
3.3 |  | Polling Place Information Officer costs
3.4 |  | Equipment to mark 2m spacing where needed
3.5 |  | Quantities of voting pencils
3.6 |  | Additional reserve polling staff
4.1 | E-Count Costs | Bigger venue / longer booking period
4.2 |  | Additional Monitors (x4 for adjudication, x1 large screen for RO adjudication)
Protective plastic barriers for customer facing staff
4.3 |  | People to move boxes and trays at the count
4.4 |  | Additional reserve count staff
5.1 | Insurance | Consider what insurance arrangements are in place locally in the event of a postponed by-election where costs have been incurred

## Supply Chain
Elections and Covid-19 - SUPPLY CHAIN
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1 | Printer; Printing Poll Cards, Postal Votes and Ballot Papers | Have you made contact with your provider to ensure capacity and appropriate contingency arrangements.
2 | PVMS, E-Count | Have you made contact with your provider to ensure capacity and appropriate contingency arrangements.
3 | Royal Mail | Have you made contact with Royal Mail to understand service status and arrangements in place?
If there is the potential to effect the postal vote delivery process, do you have contingency arrangements in place?
4 | Other Election Equipment Suppliers | Have you checked current stocks held and availability of equipment required? For example, polling station sundry packs.
5 | Equipment Sharing | Have you considered the sharing of any necessary new equipment purchases with neighbouring election teams? For example, plastic barriers for polling stations.
6 | Logistics (e.g. equipment delivery) | Have you made contact with your provider to ensure capacity and appropriate contingency arrangements.

## Venues
Covid-19 - VENUES
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required |  |  |  | Date Updated | Status
[5 empty] | Postal Vote Opening | Ballot Box Preparation | Polling Places | The Count
1.1 | All Venues | Have you made a booking enquiry of the existing venue(s) and is it available for the by-election?
Have you plans in place for back-up venues?
Are you aware what other activities are taking place in the building at the same time and have taken account of these in terms of distancing requirements?
1.2 |  | Is the venue big enough to accommodate social distancing requirements?
1.3 |  | Will the venue allow the use of floor markings required to maintain social distancing?
1.4 |  | What information signage is required outside and inside the venue?
1.5 |  | Have you procedures in place for cleaning of the venue on initial occupation?
1.6 |  | Have you procedures in place for regular cleaning and sanitising throughout the period of use?
1.7 |  | Have you considered how you can increase ventilation where it is possible and safe to do so?
1.8 |  | Have you procedures in place for the provision of cleaning and sanitising products?
Have you procedures in place for the provision of catering if required?
1.9 |  | Have you made an assessment of how long the venue needs to be booked for? (Does the booking period need to be longer? I.e. polling place required from day before to set up, sanitise, mark floor for social distancing, etc.)
1.10 |  | Are procedures in place to keep all entry and exit doors open throughout the period of use?
1.11 |  | Have you plans in place to record the contact details of all in attendance if required for contact tracing purposes?
2.1 | Polling Places | Are schools available to be used?
2.2 |  | Is it necessary to increase the number of polling stations or places in any areas?

## Workforce Protection & Planning
Elections and Covid-19 - WORKFORCE PROTECTION & PLANNING
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1 | Ability to fully staff all positions | Have you considered early communication with staff to understand your ability to staff the election?
Have you been able to staff positions from established elections staff?
Do you require to seek the formal agreement of the Local Authority to make its staff available to the Returning Officer?
Have you considered the use of the Local Authorities Covid Volunteers Staff Database?
2 | Staff who are vulnerable or at risk | Have you an agreed procedure in place to deal with staff who are in high risk categories?
If appropriate have you identified staff who in a high risk age group?
Are you taking steps to identify staff who are in other high risk groups?
3 | Reserve Staff | Have you determined how many reserve staff for each position are required?
Have reserve staff been recruited?
Has the cost of reserve staff been included in financial planning?
4 | Additional Staff | Have you identified those areas where additional or new types of staff may be required? For example, Information Officers at Polling stations, the presence of more senior staff at Polling Stations.
5 | DRO's / Core Election Staff | Do you have contingency plans in place for absence of senior election staff?
Do you have processes in place for internal staff to cover the absence of senior elections staff?
Do you have in place a reciprocal agreement in place with a neighbouring election team?
6 | RO Liability / Duty of Care | Have you taken advice regarding RO liability and Coronavirus?
Have you an agreed procedure in place to deal with voters or other customers who present with visible symptoms of coronavirus?
7 | Health & Safety Advice | Have you taken the advice of Health and Safety colleagues regarding procedures to be followed to protect all staff?

## Electoral Registration
Elections and Covid-19 - ELECTORAL REGISTRATION
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1 | Election Timetable | Have you agreed the by-election timetable with the ERO? |  |  | Note the extension to the franchise to include foreign nationals and eligible prisoners and any effect this may have on registration, volumes and processes.
1.1 |  | Are there agreed dates for production of registers and street lists and arrangements in place for these to be delivered or picked-up?
2 | Data Transfer Timetable | Have you agreed the timetable for other operational parts of the election such as the schedule for transfer of data? |  |  | Consider flexibility in the timetable and ERO contingency planning in order to deal with a last minute spike in registration.
3 | Absent vote applications | Have you confirmed the capacity of the ERO to deal with an increase in postal vote applications and understood and taken account of any consequence this may have? |  |  | Has the ERO capacity in both staffing and space to accommodate more staff if required?
4 | Poll Cards | Have you agreed the format of poll cards? In particular, there may be a need to ensure poll cards display the name of the specific station. |  |  | Discuss the practicalities and implications of displaying the name of the specific station with ERO and print suppliers.
5 | Communications | Have you agreed a communications plan with the ERO around registrations, timescales, the voting process and communications with the public. |  |  | There needs to be clear communication to the electorate on how to engage with ERO staff; e.g. is the ERO's office open to the public, is it on an appointment only basis?
6 | Polling Station Registers, street lists, etc | Have you agreed the format of the stationery to be produced and provided by the ERO?
7 | Day of Poll | Have you an agreed list of contacts for both ERO and RO?
8 | Emergency Proxies / Clerical Errors | Have you clarified the protocol for dealing with Emergency Proxies and Clerical Errors under Covid conditions?

## Nominations
Issue Log - Elections and Covid-19 - NOMINATIONS
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1.1 | Political Party, Candidate and Agent Liaison | Have you communicated the process for nominations to political parties and prospective candidates and agents?
1.2 |  | Have you requested nomination packs are downloaded and printed where possible?
1.3 |  | Have you requested that appointments are made for in-person submission?
1.4 |  | Have you requested full contact details are provided to facilitate the process?
2 | Informal Checks | Have you developed and communicated an electronic process for informal checks?
3.1 | Submission In-person of Nomination Forms | Have you booked a suitable room or space to receive nomination papers in person? |  |  | The working group noted this would reduce the interaction necessary when an in-person visit was made for formal submission.
3.2 |  | Have you planned the layout for the room and ensured it is big enough to meet distancing requirements?
4 | Inspection | Have you a process for the inspection of nomination papers?

## Voting In-Person
Elections and Covid-19 - VOTING IN PERSON
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1.1 | Voting Process | Do you have a procedure document describing the voting process which incorporates social distancing rules?
1.2 |  | Have you made an assessment of the maximum number of people to be permitted to each polling place / polling station queue at any one time?
1.3 |  | Is there a queueing procedure which incorporates floor markings inside and outside of the building and a one-way system for entry and exit?
1.4 |  | Are pens or pencils to be provided and will voters be asked to bring their own if possible?
1.5 |  | How many compartments of the polling booth will be made available to use?
1.6 |  | Have you a procedure in place for the use and disposal of poll cards?
2.1 | Cleaning / Infection Prevention and Control | Do you have a procedure in place for cleaning the building and polling equipment initially, throughout use and at the end of use?
2.2 |  | Do you have a procedure in place for the use of hand sanitiser on entrance to the polling place?
2.3 |  | Have you ensured that hand washing facilities are present?
2.4 |  | Have you ensured the building will have adequate ventilation?
2.5 |  | Will there be a barrier screen between staff and voters at the polling desk?
2.6 |  | Will voters be asked to wear face coverings?
2.7 |  | Do you have a process in place to follow should a voter refuse to wear a face covering?
2.8 |  | Will staff be asked to wear face coverings and will these be provided?
3.1 | Staffing | Have you made an assessment of the staffing required at polling places and will additional staff be required, for example Information Officers?
3.2 |  | Have you made an assessment of the physical demands the revised procedures have on staff and is a shift system required?
4.1 | Voters in the Shielding / Higher Risk Categories | Do you have a procedure in place to communicate with those in the High Risk categories?
4.2 |  | Is specific guidance issued reminding those in the shielding category not to attend polling stations?
4.3 |  | Will you display posters at the polling place reminding those in the shielding category not to attend?
5 | General Covid-19 Information Posters | Are there general Covid-19 information posters outlining the procedures in place at the polling station and does it ask voters with symptoms not to enter?

## Absent Voting
ABSENT VOTING
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1.1 | Process | Do you have a procedure document describing postal vote opening sessions which incorporates social distancing rules as required?
2.1 | Increase in Volume of Postal Votes | Do you have plans in place to manage the likely increase in the volume of replacements?
2.2 |  | Do you have plans in place to manage the likely increase in the volume of customer contacts?
2.3 |  | Do your plans for postal vote opening sessions take account of the increase in resources required including time, venue size, staffing and process.
3.1 | Communications | Do you have plans in place to communicate voting options and procedures with the electorate?
3.2 |  | Have you agreed procedures and communications with the ERO?
4.1 | Health & Safety | Do you have procedures in place for the receipt, storage and opening of postal votes? |  |  | Idox are unable to provide self-seal envelopes for the by-elections.
4.2 |  |  |  |  | Health and Safety advice indicates that risks of virus transmission are significantly reduced if paper documents can be left for 24 hours after receipt before being touched.

## The Count
Elections and Covid-19 - THE COUNT
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1 | Process | Do you have a procedure document to describe how the count will operate within the rules of social distancing?
1.1 | Timing | Have you agreed a count start time? |  |  | Consensus amongst the working group for a next day count.
2 | Venue | Have you identified a suitable venue with the necessary increased space requirements?
3 | Training | Do you have a count training plan with time and venue allocated?
4 | Staffing | Have you identified revised staffing requirements?
Has staffing of the count been completed?
5 | Equipment | Have you identified the additional equipment that may be required for revised count arrangements? E.g. barriers, additional ICT equipment
6 | Contact Tracing | Do you have a process in place to record the contact details of all present, to be used for contact tracing if necessary?

## Communications
Elections and Covid-19 - Communications
No. | Description | Details | Date Identified | Owner | Latest Position / Action Required | Date Updated | Status
1 | Have you developed a Communications Plan?
1.1 | Communication with electors outlining options and procedures for voting. |  |  |  | By-elections group discussed writing to all electors / leaflets to all households. Consider the use of social media and all online channels.
1.2 | Communications with political parties, candidates and agents. |  |  |  | Advise of the arrangements in place at the elections and procedures to be followed. Develop briefing resources which utilise online platforms.
1.3 | Communications with the media.
1.4 | Communication with SPOC